## Proposed activity of project KRANTI (15th August 2026 -14 August 2027)

| Activity | Duration |
| --- | --- |
| Selection of model village, community consultations, formation of Project Implementation Team (PIT), baseline village information collection | 15th August …….. |
| Organization of spiritual camps, community meetings, introduce Maitri Bhoj gatherings, awareness on Gram Swaraj and participatory governance | 1st September….2nd Oct |
| Practical training of rural youth, preparation of social maps, resource maps, and problem maps, awareness on government schemes, establishment of e-information bank | 25th September ……… 30th November |
| Study and documentation of functioning of Gram Sabha, Gram Panchayat committees, SHGs, MGNREGA activities, and social audit processes | 15th November ………… 2nd February |
| Identification of priority village issue, formation of working groups, interface meetings with government departments, development of action plan, strengthening collaboration between SHGs and Gram Panchayat | 3rd December …………2nd February |
| Implementation of community action initiatives, regular Gram Sabha, documentation of progress, updates on project website and presentation of findings in open meetings with community and Govt. officials | 2nd October …………………………………. |
| Monitoring activities of SHG and MGNREGA. Planning for involving people and institution to join hands in developing a village as live model on process. | Continuous activities throughout the project period |
| Maitri Bhooj (Community dinners) on every Pooranmasi and Amawasya for feedback and dialogue to document state of village electronically. |  |
| Open meeting of community (Gram Sabha) |  |
| Website updates |  |
| Final evaluation workshop Presentation of project reports, documentation of best practices, preparation for KRANTI Phase II for replication of best practices. | 11 – 15 August 2027 |